## Sheet1
Product Backlog ID | Source | User Story ID | User Story Name | User Story Description | Scrum Team Assigned | Time Estimate | Comments
1 |  | US:1 | login using user cred | Login as a administrator, manager according to that page will be open | Yash | 2 hrs
2 |  | US:2 | add manager | Here we can add new manager | Yash | 2 hrs
3 |  | US:3 | update manager | Here we can update the manager details | Yash | 1hrs
4 |  | US:4 | view managers | View the managers in the company | Yash | 1 hrs
5 |  | US:5 | delete manager | Delete the manager from the list or database | Yash | 1 hrs
6 |  | US:6 | count assets | Give the count of assets available | Yash | 2 hrs
7 |  | US:7 | add asset | Administrator can add the assets | Yash | 2 hrs
8 |  | US:8 | update asset | If the details or name sometimes get incorrect administrator can edit it also | Yash | 1 hrs
9 |  | US:9 | delete asset | If administrator wants to delete the asset from the database | Yash | 1 hrs
10 |  | US:10 | change status | Change asset status to allocated | Aditya | 1 hrs
11 |  | US:11 | check if unallocated | Check whether an asset is unallocated or not | Aditya | 1 hrs
12 |  | US:12 | search asset | Check whether the asset is available or not | Aditya | 1 hrs
13 |  | US:13 | add employee | Adding the employee by adding details of the employee | Sonali | 1 hrs
14 |  | US:14 | update employee | Update employee details in the databse | Sonali | 1 hrs
15 |  | US:15 | delete employee | Delete employee from the database | Sonali | 1 hrs
16 |  | US:16 | search employee | Search the employee by it's ID and Name | Sonali | 1 hrs
17 |  | US:17 | View allocation reqs | View the request raise by the manager for assets | Aditya | 1 hrs
18 |  | US:18 | View pending reqs | View all the pending requests | Aditya | 1 hrs
19 |  | US:19 | raise req | Raise request to the administrator for assets | Aditya | 1 hrs
20 |  | US:20 | Change status | Change the assets of allocation | Aditya | 1 hrs
21 |  | US:21 | Integration of front end with | here all activities done by participant administrator, manager will save in the backend | Aditya
backend